## PRODUCT BACKLOG
Monopoly Game
PRODUCT BACKLOG
User Story ID | User Story | Estimate (size) | Priority | Sprint
US001 | The winner will be the wealthiest player through buying, renting and selling property. If all Players agree to end game, the winner is the wealthiest Player. If all but one player has gone bankrupt then that Player is the winner | Small | 4
US002 | A game must have 2 to 4 Players. | Small | 3
US003 | The Banker is not a Player, it a separate entity | Medium | 3
US004 | One of the 2 to 4 players must be a Player simulated by the computer | Large | 4
US005 | The Game Board consists of a sequence of Game Board elements and space for the Community Chest and Chance Card decks. | Large | 1 | 1
US006 | A Game Board element is a GO space, Property spaces, Community Chest space, Chance space, Jail space, Railroad spaces, Free Parking space, Electric Company space, Water Works space, Luxury Tax space, Income Tax space, and Goto Jail space | Medium | 1 | 1
US007 | A Game Board element has a collections of Tokens that currently occupy that element and a sequence of actions that occur for Players who land on each element. | Small | 1 | 1
US008 | A Player has a Token, board position, Money, and a collection of owned properties. | Medium | 2
US009 | Movement of Player Tokens is controlled by the roll of 2 six-sided die. A Player's token is moved the number of Board Spaces indicated by the sum of the two die. If a player roll doubles then they can move again. If a Player rolls doubles 3 times in a row then they goto Jail | Small | 1 | 1
US010 | The Banker has an infinte amount of Money, a Collection of Property Title Deeds, a Collection of Houses, Collection of Hotels, and a collection of Mortgaged Properties. The Banker sells Properties, Houses, and Hotels. The Banker performs auctions for Properties. The Banker mortgages Properties. | Large | 4
US011 | Implement a Player's turn | Medium | 5
US012 | Implement a collection of all Players | Small | 2
US013 | Chance Cards is a deck of cards that contain actions that will occur when a card is drawn from the deck | Medium | 1 | 1
US014 | Community Chest Cards is a deck of cards that contain actions that will occur when a card is drawn from the deck | Medium | 1 | 1
US015 | Player Tokens are a set of objects including Top hat, Thimble, Iron, Boot, Battleship, Cannon, Race car, Scottie dog, Wheelbarrow. | Small | 2
US016 | Property Title Deed Cards is a deck of cards that contain all information regrading a property, such as, Color, Name, Basic Rent, Number of Houses, Rent with 1 – 4 houses, Rent with Hotel, Mortgage Value, House cost, Hotel cost | Medium | 4
US017 | Implement Houses | Small | 4
US018 | Implement Hotels | Small | 4
US019 | Implement Money | Small | 2
US020 | The Game State has a Game Board, collection of Players, Dice, and a Banker. The Game State implements the interface to the View (GUI). The Game State implements the actions of a Player's Turn. The Game State initializes a new game by creating a Game Board, allowing each Player to choose a Token, and Allocating $1,500 from the Bank to each Player. | Large | 5
US021 | The Computer Controlled Player will simulate the actions of a Human Player. It will make decisions based on Random Number and set percentages. It will have several strategies depending on its current state that can be changed dynamically. | Large | 5
US022
US023
US024
US025
US026
US027
US028
US029
US030
US031
US032
US033
US034
US035
US036
US037
US038
US039
US040
US041
US042
US043
US044
US045
US046
US047
US048
US049
US050
US051
US052
US053
US054
US055
US056
US057
US058
US059
US060
US061
US062
US063
US064
US065
US066
US067
US068
US069
US070
US071
US072
US073
US074
US075

## PROJECT DETAILS
PROJECT NUMBER | 1
PROJECT NAME | Monopoly Game
PROJECT MANAGER | Greg Schaper
DATE | 2025-02-17
VERSION | 1

## DROPDOWN MENUS
PRIORITY | SPRINT
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6
7
8
9
10
TO EDIT THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Source to match the values you want to appear in the menu.
TO DELETE THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Allow to Any value.

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel