## Sprint 1 Backlog
AGILE SPRINT 1 BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
The Game Board consists of a sequence of Game Board elements and space for the Community Chest and Chance Card decks. |  |  | Complete
Implement Community Chest & Chance Cards |  | Anthony Dayoub | Done | 3 hours
Implement the list of properties |  | Angel Lopez | Done | 3 hours
Implement Token dummy class |  | Amanda McNesby | Done | 3 hours
Implement boardSquare class |  | Jennifer Alicea | Done | 3 hours
A Game Board element is a GO space, Property spaces, Community Chest space, Chance space, Jail space, Railroad spaces, Free Parking space, Electric Company space, Water Works space, Luxury Tax space, Income Tax space, and Goto Jail space |  |  | Complete | 4 hours
Implement Go space, Jail space, free parking space, and go to Jail space |  | Amanda McNesby | Done
Implement Electric Company Space and Water Works space |  | Angel Lopez | Done
Implement railroad spaces |  | Angel Lopez | Done
Implement Luxury Tax space and Income Tax space |  | Jennifer Alicea | Done
Implement Chance and Community Chest Spaces |  | Anthony Dayoub | Done
A Game Board element has a collections of Tokens that currently occupy that element and a sequence of actions that occur for Players who land on each element. |  | Amanda McNesby | Completed | 1 hour
create a constructor for the token |  | Amanda McNesby | Done
implement method to assign token to player |  | Amanda McNesby | Done
implement method to assign token to a position on the board |  | Amanda McNesby | Done
Implement tokens enum class |  | Amanda McNesby | Done
Movement of Player Tokens is controlled by the roll of 2 six-sided die. A Player's token is moved the number of Board Spaces indicated by the sum of the two die. If a player roll doubles then they can move again. If a Player rolls doubles 3 times in a row then they goto Jail |  |  | Completed
Implement roll method |  | Anthony, Amanda, Angel, and Jennifer | Done
Chance Cards is a deck of cards that contain actions that will occur when a card is drawn from the deck
Created an ArrayList for Chance Cards |  | Anthony Dayoub | Done
Added effects for Chance Cards |  | Anthony Dayoub | Done
Added a draw and shuffle method to draw chance cards |  | Anthony Dayoub | Done
Implemented Chance Cards |  | Anthony Dayoub | Done
Community Chest Cards is a deck of cards that contain actions that will occur when a card is drawn from the deck |  |  | Completed
Created an ArrayList for Chest Cards |  | Anthony Dayoub | Done
Implemented Chest Cards |  | Anthony Dayoub | Done
Added a draw and shuffle method for chest cards |  | Anthony Dayoub | Done
Added effects for Chest Cards |  | Anthony Dayoub | Done
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Goal
Sprint 1 Goal
Implement the Model for the Game Board.

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
Add rows and columns as needed.
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0